## Sheet1
Product Backlog - Group G
Sprint ID | Task ID | Description | Owner | Estimated time | Completed? | Key
1 | 1 | Git Hub Project for Coursework Set Up | Team | 1 day | Yes | Name | Abbreviation
1 | 2 | Code of Conduct | CN + Team | 1 day | Yes | Chris Nelis | CN
1 | 3 | Product Backlog Creation | RW + MG | 1 day | Yes | Kai Mainz | KM
1 | 4 | Project builds to self-contained JAR with Maven | KM + MG | 1 day | Yes | Murray Gillespie | MG
1 | 5 | Dockerfile for Project set up and works. | KM + CN | 1 day | Yes | Ross Worton | RW
1 | 6 | Travis CI Integration | KM | 1 day | Yes
1 | 7 | Correct Branches for Gitflow and Workflow Created | KM + RW | 1 day | Yes
1 | 8 | First Release created | KM | 1 day | Yes
2 | 1 | Gain knowledge on how to implement the SQL database | Team | 2 days | No
2 | 2 | Integrate project with Zube.io | tbc | tbc | No
2 | 3 | Creation of Project Boards | tbc | tbc | No
2 | 4 | Sprint Board Creation | tbc | tbc | No
2 | 5 | Use Diagram Creation | tbc | tbc | No
2 | 6 | Gain information and implement User Stories | tbc | tbc | No
3 | 1 | Unit Tests Defined | tbc | tbc | No
3 | 2 | Test Driven Devolpment created | tbc | tbc | No
3 | 3 | Travis CI Testing | tbc | tbc | No
4 | 1 | Working Deployment | tbc | tbc | No
4 | 2 | Bug reporting system set-up | tbc | tbc | No